## Slide 1: Integrated Power Development Scheme ( IPDS )
    BRIEF OF PROJECT
Govt. of India has launched Integrated Power Development Scheme (IPDS) for Urban area (Statutory Towns) only. As per Census 2011, 254 No. Of Towns having population more than 15000, are considered under IPDS.
    OBJECTIVES
      24 X 7 Hrs Power supply for consumers
      Providing access to all Urban Households
    FINANCIAL SCOPE
Provision of funds : 60% Grant Central Government.
10% Utility/ State Government
30% Loan from FIs/ Banks
    MoP has approved Rs. 2300.43 Crs as final DPR amount for 45 Circles in 35 Districts in Maharashtra
    IPDS Tender Status
Tender Status | Part I |  |  | Part II |  |  | Total |  | 
 | Count | Tender Amount | LOA Amount | Count | Tender Amount | LOA Amount | Count | Tender Amount | LOA Amount
 |  | (In Crs) | (In Crs) |  | (In Crs) | (In Crs) |  | (In Crs) | (In Crs)
LOAs Issued | 48 | 872 | 864 | 66 | 1392 | 1438 | 114 | 2264 | 2302

## Slide 2: Sanctioned Scope of Work under IPDS ( 2300.43 Crs )
Sr. No. | Circle | DPR Cost | New Substation | Augmentation of Power T/F | Additional power T/F | HT Line | LT Line | New DTC Total | DTC Aug Total
 |  | Crs | No | No | No | Km | Km | No | No
1 | Akola | 17.96 | 2 | 0 | 0 | 57.48 | 28.30 | 52.00 | 18.00
2 | Buldhana | 17.35 | 3 | 0 | 0 | 47.50 | 26.60 | 47.00 | 8.00
3 | Washim | 12.92 | 1 | 0 | 0 | 31.66 | 50.76 | 68.00 | 22.00
4 | Amravati | 124.38 | 7 | 4 | 0 | 425.72 | 128.00 | 204.00 | 63.00
5 | Yavatmal | 13.11 | 2 | 0 | 0 | 33.16 | 26.09 | 44.00 | 10.00
6 | Bhandara | 16.79 | 1 | 0 | 0 | 62.35 | 43.00 | 73.00 | 47.00
7 | Gondia | 28.21 | 3 | 3 | 3 | 84.00 | 53.85 | 75.00 | 75.00
8 | Chandrapur | 68.74 | 8 | 0 | 0 | 212.00 | 107.00 | 208.00 | 63.00
9 | Gadchiroli | 27.80 | 3 | 0 | 1 | 109.50 | 59.55 | 57.00 | 61.00
10 | Wardha | 34.87 | 3 | 2 | 4 | 104.30 | 20.50 | 98.00 | 52.00
11 | Nagpur U | 198.15 | 5 | 0 | 1 | 529.80 | 256.80 | 157.00 | 30.00
12 | Nagpur R | 119.38 | 1 | 4 | 0 | 410.25 | 961.60 | 136.00 | 31.00
13 | Latur | 56.40 | 1 | 4 | 0 | 126.46 | 186.51 | 213.00 | 130.00
14 | Beed | 48.16 | 0 | 8 | 1 | 101.21 | 167.19 | 252.00 | 180.00
15 | Osmanabad | 65.82 | 7 | 2 | 1 | 333.70 | 250.05 | 190.00 | 157.00
16 | Nanded | 91.35 | 4 | 4 | 2 | 332.92 | 208.60 | 197.00 | 70.00
17 | Hingoli | 29.98 | 2 | 0 | 0 | 180.93 | 185.62 | 83.00 | 53.00
18 | Parbhani | 63.40 | 9 | 0 | 0 | 146.05 | 155.62 | 137.00 | 133.00
19 | Auranagbad U | 111.09 | 6 | 3 | 2 | 202.52 | 153.70 | 256.00 | 330.00
20 | Auranagbad R | 29.87 | 1 | 0 | 0 | 119.93 | 122.00 | 161.00 | 76.00
21 | Jalna | 35.08 | 3 | 0 | 2 | 106.80 | 183.98 | 86.00 | 43.00
22 | Jalgaon | 100.66 | 7 | 6 | 2 | 338.00 | 312.28 | 402.00 | 245.00

## Slide 3: Sanctioned Scope of Work under IPDS ( 2300.43 Crs )
Sr. No. | Circle | DPR Cost | New Substation | Augmentation of Power T/F | Additional power T/F | HT Line | LT Line | New DTC Total | DTC Aug Total
 |  | Crs | No | No | No | Km | Km | No | No
23 | Dhule | 59.31 | 5 | 2 | 0 | 175.17 | 231.76 | 337.00 | 211.00
24 | Nandurbar | 38.10 | 4 | 2 | 1 | 165.50 | 62.00 | 123.00 | 135.00
25 | Ahmednagar | 85.41 | 8 | 5 | 1 | 366.50 | 183.72 | 233.00 | 147.00
26 | Nashik U | 30.60 | 3 | 1 | 0 | 161.10 | 100.20 | 94.00 | 69.00
27 | Nashik R | 65.65 | 6 | 0 | 1 | 171.67 | 12.00 | 157.00 | 129.00
28 | Bhiwandi | 31.47 | 0 | 0 | 0 | 24.70 | 41.40 | 33.00 | 46.00
29 | Thane U | 59.14 | 2 | 0 | 0 | 63.85 | 51.60 | 122.00 | 19.00
30 | Vashi | 20.65 | 0 | 0 | 0 | 4.00 | 139.00 | 10.00 | 30.00
31 | Ratnagiri | 38.98 | 0 | 1 | 1 | 125.06 | 209.00 | 107.00 | 83.00
32 | Sindhudurg | 40.32 | 1 | 0 | 0 | 138.83 | 111.64 | 54.00 | 30.00
33 | Kalyan I | 64.03 | 1 | 0 | 0 | 40.00 | 146.00 | 121.00 | 158.00
34 | Kalyan II | 52.03 | 3 | 0 | 0 | 105.00 | 137.48 | 55.00 | 70.00
35 | Vasai | 94.65 | 5 | 0 | 0 | 273.30 | 162.46 | 137.00 | 26.00
36 | Pen | 21.63 | 0 | 0 | 0 | 31.00 | 244.45 | 30.00 | 28.00
37 | Baramati | 26.65 | 0 | 0 | 1 | 42.30 | 148.40 | 90.00 | 33.00
38 | Satara | 26.84 | 1 | 1 | 0 | 87.23 | 31.49 | 55.00 | 99.00
39 | Solapur | 27.11 | 0 | 1 | 1 | 73.86 | 113.28 | 165.00 | 116.00
40 | Rastapeth | 71.35 | 6 | 0 | 0 | 174.95 | 14.00 | 91.00 | 15.00
41 | Ganeshkhind | 36.00 | 3 | 0 | 0 | 71.16 | 28.35 | 99.00 | 0.00
42 | Pune R | 9.69 | 0 | 0 | 0 | 33.50 | 26.00 | 29.00 | 10.00
43 | Kolhapur | 56.4656 | 2 | 0 | 0 | 178.39 | 279.81 | 214.00 | 187.00
44 | Sangli | 32.89 | 0 | 3 | 0 | 90.14 | 152.00 | 80.00 | 106.00
Total |  | 2300.43 | 129.00 | 56.00 | 25.00 | 6693.45 | 6313.62 | 5632.00 | 3644.00

## Slide 4: IPDS Work Status Sept 2021
Particulars | Unit | Freezed Scope | Completed / Commissioned | % Progress
New Substation | Nos | 120 | 120 | 100
Augmentation of PTF | Nos | 68 | 68 | 100
Add. Power Transformer | Nos | 32 | 32 | 100
HT Line (OH+UG) | Km | 4555 | 4555 | 100
LT Line (OH+UG) | Km | 2842 | 2842 | 100
New DTC | Nos | 5057 | 5057 | 100
Augmentation of DTC | Nos | 4118 | 4118 | 100

## Slide 5: Region Wise Summary – Nagpur Region
Sr No | Zone | Circle | LOA Cost (Rs In Crs) | Scheme Cost (In Rs Crs.) | New Substation |  | Augmentation Power of Transformer |  | Additional of Power Transformer |  | New DTC |  | DTC Augmentation |  | LT Line |  | HT Line |  | % Progress
 |  |  |  |  | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | 
1 | Amravati | Yavatmal | 12.36 | 13.11 | 2 | 2 | 0 | 0 | 0 | 0 | 57 | 57 | 10 | 10 | 10 | 10 | 29 | 29 | 100%
2 |  | Amravati | 121.94 | 124.38 | 7 | 7 | 5 | 5 | 0 | 0 | 201 | 201 | 102 | 102 | 116 | 116 | 284 | 283 | 100%
 | Amravati Total |  | 134 | 137.49 | 9 | 9 | 5 | 5 | 0 | 0 | 258 | 258 | 112 | 112 | 126 | 126 | 313 | 312 | 100%
3 | Chandrapur | Chandrapur | 64 | 68.74 | 7 | 7 | 0 | 0 | 0 | 0 | 127 | 127 | 83 | 83 | 28 | 28 | 123 | 123 | 100%
4 |  | Gadchiroli | 32 | 27.80 | 3 | 3 | 0 | 0 | 1 | 1 | 56 | 56 | 62 | 62 | 16 | 16 | 77 | 77 | 100%
 | Chandrapur Total |  | 96 | 96.54 | 10 | 10 | 0 | 0 | 1 | 1 | 183 | 183 | 145 | 145 | 43 | 43 | 200 | 200 | 100%
5 | Akola | Akola | 21 | 17.96 | 2 | 2 | 0 | 0 | 0 | 0 | 43 | 43 | 20 | 20 | 10 | 10 | 37 | 37 | 100%
6 |  | Buldhana | 20 | 17.35 | 3 | 3 | 0 | 0 | 0 | 0 | 42 | 42 | 11 | 11 | 6 | 6 | 31 | 31 | 100%
7 |  | Washim | 15 | 12.92 | 1 | 1 | 0 | 0 | 0 | 0 | 68 | 68 | 22 | 22 | 22 | 22 | 16 | 16 | 100%
 | Akola Total |  | 55 | 48.22 | 6 | 6 | 0 | 0 | 0 | 0 | 153 | 153 | 53 | 53 | 38 | 38 | 84 | 84 | 100%
8 | Nagpur | Nagpur R | 113 | 119.38 | 1 | 1 | 5 | 5 | 0 | 0 | 133 | 133 | 18 | 18 | 249 | 249 | 341 | 341 | 100%
9 |  | Nagpur U | 133 | 141.07 | 4 | 4 | 0 | 0 | 1 | 1 | 157 | 157 | 214 | 214 | 311 | 311 | 553 | 553 | 100%
10 |  | Nagpur DF | 57 | 57.08 | 3 | 3 | 0 | 0 | 3 | 3 | 191 | 191 | 98 | 98 | 64 | 64 | 148 | 148 | 100%
11 |  | Wardha | 37 | 34.87 | 3 | 3 | 2 | 2 | 4 | 4 | 82 | 82 | 43 | 43 | 9 | 9 | 101 | 101 | 100%
 | Nagpur Total |  | 340 | 352.40 | 11 | 11 | 7 | 7 | 8 | 8 | 563 | 563 | 373 | 373 | 633 | 633 | 1143 | 1143 | 100%
12 | Gondia | Bhandara | 20 | 16.79 | 1 | 1 | 0 | 0 | 0 | 0 | 68 | 68 | 52 | 52 | 21 | 21 | 35 | 35 | 100%
13 |  | Gondia | 33 | 28.21 | 3 | 3 | 3 | 3 | 3 | 3 | 73 | 73 | 74 | 74 | 23 | 23 | 63 | 63 | 100%
 | Gondia Total |  | 53 | 44.99 | 4 | 4 | 3 | 3 | 3 | 3 | 141 | 141 | 126 | 126 | 44 | 44 | 97 | 97 | 100%
 | Nagpur Total |  | 678 | 680 | 40 | 40 | 15 | 15 | 12 | 12 | 1298 | 1298 | 809 | 809 | 884 | 884 | 1838 | 1837 | 100%

## Slide 6: Region Wise Summary – Aurangabad Region
Sr No | Zone | Circle | LOA Cost (Rs In Crs) | Scheme Cost (In Rs Crs.) | New Substation |  | Augmentation of Power Transformer |  | Additional of Power Transformer |  | New DTC |  | DTC Augmentation |  | LT Line |  | HT Line |  | % Progress
 |  |  |  |  | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | 
14 | Nanded | Hingoli | 28 | 29.98 | 2 | 2 | 0 | 0 | 0 | 0 | 80 | 80 | 53 | 53 | 80 | 80 | 55 | 55 | 100%
15 |  | Nanded | 91 | 91.35 | 4 | 4 | 4 | 4 | 2 | 2 | 197 | 197 | 68 | 68 | 161 | 161 | 157 | 157 | 100%
16 |  | Parbhani | 68 | 63.40 | 5 | 5 | 2 | 2 | 3 | 3 | 103 | 103 | 133 | 133 | 43 | 43 | 100 | 100 | 100%
 | Nanded Total |  | 187 | 184.74 | 11 | 11 | 6 | 6 | 5 | 5 | 380 | 380 | 254 | 254 | 284 | 284 | 313 | 313 | 100%
17 | Latur | Beed | 47 | 48.16 | 0 | 0 | 8 | 8 | 1 | 1 | 244 | 244 | 163 | 163 | 112 | 112 | 48 | 48 | 100%
18 |  | Latur | 59 | 56.40 | 1 | 1 | 4 | 4 | 0 | 0 | 205 | 205 | 130 | 130 | 102 | 102 | 145 | 145 | 100%
19 |  | Osmanabad | 69 | 65.82 | 7 | 7 | 2 | 2 | 0 | 0 | 147 | 147 | 135 | 135 | 139 | 139 | 142 | 142 | 100%
 | Latur Total |  | 175 | 170.37 | 8 | 8 | 14 | 14 | 1 | 1 | 596 | 596 | 428 | 428 | 353 | 353 | 334 | 334 | 100%
20 | Auranagbad | Aurangabad U | 106 | 111.09 | 5 | 5 | 7 | 7 | 2 | 2 | 242 | 242 | 306 | 306 | 46 | 46 | 119 | 119 | 100%
21 |  | Aurangabad R | 34 | 29.87 | 1 | 1 | 0 | 0 | 0 | 0 | 135 | 135 | 86 | 86 | 53 | 53 | 45 | 45 | 100%
22 |  | Jalna | 36 | 35.08 | 3 | 3 | 2 | 2 | 1 | 1 | 86 | 86 | 56 | 56 | 55 | 55 | 48 | 48 | 100%
 | Auranagbad Total |  | 176 | 176.04 | 9 | 9 | 9 | 9 | 3 | 3 | 463 | 463 | 448 | 448 | 153 | 153 | 213 | 213 | 100%
 | Auranagbad Total |  | 538 | 531 | 28 | 28 | 29 | 29 | 9 | 9 | 1439 | 1439 | 1130 | 1130 | 790 | 790 | 860 | 860 | 100%

## Slide 7: Region Wise Summary – Pune Region
Sr No | Zone | Circle | LOA Cost (Rs In Crs) | Scheme Cost (In Rs Crs.) | New Substation |  | Augmentation of Power Transformer |  | Additional of Power Transformer |  | New DTC |  | DTC Augmentation |  | LT Line |  | HT Line |  | % Progress
 |  |  |  |  | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | 
23 | Baramati | Satara | 26 | 26.84 | 1 | 1 | 1 | 1 | 0 | 0 | 42 | 42 | 95 | 95 | 8 | 8 | 50 | 50 | 100%
24 |  | Baramati | 28 | 26.65 | 0 | 0 | 0 | 0 | 1 | 1 | 38 | 38 | 22 | 22 | 85 | 85 | 37 | 37 | 100%
25 |  | Solapur | 27 | 27.11 | 0 | 0 | 0 | 0 | 2 | 2 | 150 | 150 | 108 | 108 | 78 | 78 | 36 | 36 | 100%
 | Baramati Total |  | 81 | 80.59 | 1 | 1 | 1 | 1 | 3 | 3 | 230 | 230 | 225 | 225 | 171 | 171 | 123 | 123 | 100%
26 | Pune | Pune R | 10 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 10 | 10 | 16 | 16 | 11 | 11 | 100%
27 |  | Rastapeth | 71 | 71.35 | 6 | 6 | 0 | 0 | 0 | 0 | 71 | 71 | 13 | 13 | 12 | 12 | 147 | 147 | 100%
28 |  | Ganeshkhind | 39 | 36.00 | 3 | 3 | 0 | 0 | 0 | 0 | 94 | 94 | 0 | 0 | 48 | 48 | 87 | 87 | 100%
 | Pune Total |  | 120 | 117.04 | 9 | 9 | 0 | 0 | 0 | 0 | 186 | 186 | 23 | 23 | 76 | 76 | 245 | 245 | 100%
29 | Kolhapur | Kolhapur | 68 | 56.47 | 2 | 2 | 0 | 0 | 0 | 0 | 79 | 79 | 169 | 169 | 112 | 112 | 86 | 86 | 100%
30 |  | Sangli | 28 | 32.89 | 0 | 0 | 3 | 3 | 0 | 0 | 88 | 88 | 144 | 144 | 27 | 27 | 44 | 44 | 100%
 | Kolhapur Total |  | 96 | 89.36 | 2 | 2 | 3 | 3 | 0 | 0 | 167 | 167 | 313 | 313 | 138 | 138 | 129 | 129 | 100%
 | Pune Total |  | 297 | 287 | 12 | 12 | 4 | 4 | 3 | 3 | 583 | 583 | 561 | 561 | 385 | 385 | 497 | 497 | 100%

## Slide 8: Region Wise Summary – Konkan Region
Sr No | Zone | Circle | LOA Cost (Rs In Crs) | Scheme Cost (In Rs Crs.) | New Substation |  | Augmentation of Power Transformer |  | Additional of Power Transformer |  | New DTC |  | DTC Augmentation |  | LT Line |  | HT Line |  | % Progress
 |  |  |  |  | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | Scope | Comm/Comm | 
31 | Konkan | Ratnagiri | 36 | 38.98 | 0 | 0 | 1 | 1 | 1 | 1 | 79 | 79 | 119 | 119 | 140 | 140 | 90 | 90 | 100%
32 |  | Sindhudurg | 46 | 40.32 | 1 | 1 | 0 | 0 | 0 | 0 | 33 | 33 | 30 | 30 | 38 | 38 | 80 | 80 | 100%
 | Konkan Total |  | 83 | 79.30 | 1 | 1 | 1 | 1 | 1 | 1 | 112 | 112 | 149 | 149 | 178 | 178 | 170 | 170 | 100%
33 | Jalgaon | Jalgaon | 95 | 100.66 | 7 | 7 | 6 | 6 | 2 | 2 | 326 | 326 | 215 | 215 | 53 | 53 | 187 | 187 | 100%
34 |  | Nandurbar | 37 | 38.10 | 3 | 3 | 2 | 2 | 1 | 1 | 130 | 130 | 163 | 163 | 21 | 21 | 107 | 107 | 100%
35 |  | Dhule | 64 | 59.31 | 4 | 4 | 1 | 1 | 1 | 1 | 250 | 250 | 208 | 208 | 65 | 65 | 73 | 73 | 100%
 | Jalgaon Total |  | 197 | 198.08 | 14 | 14 | 9 | 9 | 4 | 4 | 706 | 706 | 586 | 586 | 139 | 139 | 368 | 368 | 100%
36 | Kalyan | Vasai | 86 | 94.65 | 5 | 5 | 0 | 0 | 0 | 0 | 155 | 155 | 113 | 113 | 82 | 82 | 248 | 248 | 100%
37 |  | Kalyan II | 50 | 52.03 | 3 | 3 | 0 | 0 | 0 | 0 | 37 | 37 | 60 | 60 | 6 | 6 | 39 | 39 | 100%
38 |  | Kalyan I | 66 | 64.03 | 1 | 1 | 0 | 0 | 0 | 0 | 63 | 63 | 179 | 179 | 51 | 51 | 31 | 31 | 100%
 | Kalyan Total |  | 202 | 210.71 | 9 | 9 | 0 | 0 | 0 | 0 | 255 | 255 | 352 | 352 | 140 | 140 | 318 | 318 | 100%
39 | Bhandup | Bhiwandi DF | 30 | 31.47 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 107 | 107 | 9 | 9 | 25 | 25 | 100%
40 |  | Pen | 22 | 21.63 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 39 | 25 | 25 | 66 | 66 | 11 | 11 | 100%
41 |  | Vashi | 21 | 20.65 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 27 | 27 | 58 | 58 | 2 | 2 | 100%
42 |  | Thane U | 54 | 59.14 | 2 | 2 | 0 | 0 | 0 | 0 | 112 | 112 | 12 | 12 | 8 | 8 | 55 | 55 | 100%
 | Bhandup Total |  | 127 | 132.89 | 2 | 2 | 0 | 0 | 0 | 0 | 204 | 204 | 171 | 171 | 141 | 141 | 93 | 93 | 100%
43 | Nashik | Ahmednagar | 87 | 85.41 | 7 | 7 | 8 | 8 | 2 | 2 | 220 | 220 | 160 | 160 | 81 | 81 | 231 | 231 | 100%
44 |  | Malegaon | 50 | 65.65 | 4 | 4 | 0 | 0 | 1 | 1 | 154 | 154 | 131 | 131 | 14 | 14 | 86 | 86 | 100%
45 |  | Nashik U | 43 | 30.60 | 3 | 3 | 2 | 2 | 0 | 0 | 86 | 86 | 69 | 69 | 88 | 88 | 95 | 95 | 100%
 | Nashik Total |  | 180 | 181.66 | 14 | 14 | 10 | 10 | 3 | 3 | 460 | 460 | 360 | 360 | 184 | 184 | 412 | 412 | 100%
 | Konkan Total |  | 788 | 803 | 40 | 40 | 20 | 20 | 8 | 8 | 1737 | 1737 | 1618 | 1618 | 782 | 782 | 1361 | 1361 | 100%
 | Grand Total |  | 2301 | 2300 | 120 | 120 | 68 | 68 | 32 | 32 | 5057 | 5057 | 4118 | 4118 | 2842 | 2842 | 4556 | 4555 | 100%